## Blizzards
Blizzards Statement of Work
| Project Title |  | Start Date
| Study Buddies |  | 2025-11-09 |  |  | Project Duration
| Project Development Team |  | End Date |  |  | in days
| Alina (Designer), Lonzo (Tester), Robin (Lead), Samuel (SWE) |  | 2025-12-01 |  |  | 23
| User Story # | Status | Use Cases | Start Date | End Date | Duration (in days) | Comments | Status
| Alina |  |  | 2025-11-22 | 2025-12-08 | 17 |  | Not Started
| # Create profile display, schedule input, and schedule display designs | On Hold | SHA 1601da9, 4ef802, 3d45638 | 2025-11-22 | 2025-12-08 | 17 | What is this use case's user story number? If no user story, make sure you add this as a user story in our final sprint. | In Progress
Complete
On Hold
Nov 26th: 6 commits, +91, -10
| Evaluate Dr. Edwards via Class Climate | Not Started |  | 2025-11-22 | 2025-12-08 | 17
| Evaluate team using Brightspace survey | Not Started |  | 2025-12-01 | 2025-12-01 | 1
| Lonzo |  |  | 2025-11-17 | 2025-12-08 | 22
| # 43-48 Add unit tests for Profile, Schedule, Session, Flashcards, etc. | Complete | SHA 45ab501, fe680ac, d8c0295 | 2025-11-17 | 2025-11-24 | 8
| Add standup_meetings.txt File | Complete | 2c9b719 | 2025-11-20 | 2025-11-20 | 1 | This was done before we had our first user story.
| # 62 Create a remove_event method | Complete | 476de6c | 2025-11-24 | 2025-11-24 | 1
| # 62 Create an output_events method | Complete | d774f0c | 2025-11-24 | 2025-11-24 | 1
| Create two __init__.py files | Complete | 36e78ff | 2025-11-24 | 2025-11-24 | 1 | This was done for testing reasons
| Update imports in test_study_buddies.py , invite_logic.py, auto_cancel.py, main.py, test_user_profile.py, test_event.py, file | Complete | 163174a, d7b3f9b, 4e24579, 0caaac7, e06a311, c6b7d7d | 2025-11-24 | 2025-11-24 | 1 | This was done to fix our team's coding structure
| Ran tests on test_study_buddies.py file | Complete | 4d316c1 | 2025-11-24 | 2025-11-24 | 1 | This was done for testing reasons
| Remove use cases from event.py | Complete | 240e85d | 2025-11-24 | 2025-11-24 | 1 | This was done to fix our team's coding structure
| #62 Add remove_event method from User Story #62 into user_profile.py file | Complete | 7326a0e | 2025-11-24 | 2025-11-24 | 1
| #62 Add output_events method from user story #62 to user_profile.py file | Complete | 9f7e340 | 2025-11-24 | 2025-11-24 | 1
| #62 Add test_remove_event method in test_user_profile.py file | Complete | 2671261092c23eb9fcc724b87345697f502f8ba7 | 2025-11-24 | 2025-11-24 | 1
| #62 Add test_output_events method to test_user_profile.py file | Complete | 28aaca0 | 2025-11-24 | 2025-11-24 | 1
| #60 Create a remove method | Complete | 420dc3b | 2025-11-24 | 2025-11-24 | 1
| #60 Create two methods that help each other check for duplicate datetimes | Complete | 0c0d40f | 2025-11-24 | 2025-11-24 | 1
| #60 Test Study Session Use Cases | Complete | f9bcd07 | 2025-11-24 | 2025-11-24 | 1
| #59 Add User Story #59 Uses Cases to user_profile.py | Complete | 2a6d62d | 2025-11-24 | 2025-11-24 | 1
| #59 Test User Story #59 Use Cases | Complete | 9d5b2d7 | 2025-11-24 | 2025-11-24 | 1
| Remove Blizzards Modules from each .py file | Complete | 62cd261 | 2025-11-25 | 2025-11-25 | 1 | This was done to fix our team's coding structure
| #75 Create a Sort Study Sessions function from earliest to latest | Complete | 0d9b462 | 2025-11-29 | 2025-11-29 | 1
| #75 Create a function that filters only upcoming sessions | Complete | 6bc4493 | 2025-11-29 | 2025-11-29 | 1
| #75 Test sort_study_sessions function | Complete | d3f41cc | 2025-11-29 | 2025-11-29 | 1
| #75 Test upcoming sessions function | Complete | f9519ad | 2025-11-29 | 2025-11-29 | 1
| #75 Test for an empty schedule | Complete | 46a6746 | 2025-11-29 | 2025-11-29 | 1
| #76 Create Count Student Availability by Hour function in user_profile.py | Complete | 89379b9 | 2025-11-29 | 2025-11-29 | 1
| #76 Create a function that returns the hour with the highest availability | Complete | aa3d348 | 2025-11-29 | 2025-11-29 | 1
| #76 Test count_availability_by_hour method | Complete | ee2e7f8 | 2025-11-29 | 2025-11-29 | 1
| #76 Test best_hour method | Complete | 18707a1 | 2025-11-29 | 2025-11-29 | 1 |  |  | Nov 26th: 29 commits, +483, -163
| #76 Test if there is not a best hour | Complete | 462c5cb | 2025-11-29 | 2025-11-29 | 1
| #77 Create a function that checks for availability conflicts | Complete | e4a273b | 2025-11-29 | 2025-11-29 | 1
| #77 Create a function that adds a study session only if it does not conflict with another | Complete | dca2cbd | 2025-11-29 | 2025-11-29 | 1
| #77 Test that all conflict types are identified | Complete | 20508d0 | 2025-11-29 | 2025-11-29 | 1
| #77 Test that a study session is added if there are no conflicts | Complete | 54341123a32360bbb890d11ad4da1235de83585b | 2025-11-29 | 2025-11-29 | 1
| #77 Test that a study session is not added to the schedule if it conflicts with another | Complete | 99abe78 | 2025-11-29 | 2025-11-29 | 1
| Add important imports to user_profile.py & test_user_profile.py | Complete | 2941718cd258198eb10feeecf3354565bbceb5b8 | 2025-11-29 | 2025-11-29 | 1 | This was done to fix our team's coding structure
| Evaluate Dr. Edwards via Class Climate | Complete |  | 2025-11-22 | 2025-12-08 | 17
| Evaluate team using Brightspace survey | Complete |  | 2025-12-01 | 2025-12-01 | 1
| Robin |  |  | 2025-11-22 | 2025-12-08 | 17
| # Update README with 6 numbered, prioritized projects | On Hold | SHA 0228979, 837cc5e | 2025-11-25 | 2025-11-25 | 1 | What is this use case's user story number? If no user story, make sure you add this as a user story in our final sprint.
Nov 26th: 36 commits, +337, -250
| Evaluate Dr. Edwards via Class Climate | Not Started |  | 2025-11-22 | 2025-12-08 | 17
| Evaluate team using Brightspace survey | Not Started |  | 2025-12-01 | 2025-12-01 | 1
| Samuel |  |  | 2025-11-17 | 2025-12-08 | 22
| # create AutoCancelJob, FlashcardGenerator, InviteLogic, Profile, StudySession classes | On Hold | SHA d926e23, 10b580f | 2025-11-17 | 2025-11-17 | 1 | What is this use case's user story number? If no user story, make sure you add this as a user story in our final sprint.
Nov 26th: 30 commits, +461, -122
| Evaluate Dr. Edwards via Class Climate | Not Started |  | 2025-11-22 | 2025-12-08 | 17
| Evaluate team using Brightspace survey | Not Started |  | 2025-12-01 | 2025-12-01 | 1
Formulas:
Start Date = MIN([Start Date, row below]:F21)
End Date = MAX([End Date, row below]:G21)

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.
https://www.smartsheet.com/top-project-management-excel-templates?srsltid=AfmBOorM8KTqo0GkEazFKhVFp3ozfOh-BifeI1KKxQxM0WpR5p08gBRL