## Blizzards
Blizzards Statement of Work
| Project Title |  | Start Date
| Study Buddies |  | 2025-11-09 |  |  | Project Duration
| Project Development Team |  | End Date |  |  | in days
| Alina (Designer), Lonzo (Tester), Robin (Lead), Samuel (SWE) |  | 2025-12-01 |  |  | 23
| User Story # | Status | Use Cases | Start Date | End Date | Duration (in days) | Comments | Status
| Alina |  |  | 2025-11-22 | 2025-12-08 | 17 |  | Not Started
| # Create profile display, schedule input, and schedule display designs | On Hold | SHA 1601da9, 4ef802, 3d45638 | 2025-11-22 | 2025-12-08 | 17 | What is this use case's user story number? If no user story, make sure you add this as a user story in our final sprint. | In Progress
Complete
On Hold
Nov 26th: 6 commits, +91, -10
| Evaluate Dr. Edwards via Class Climate | Not Started |  | 2025-11-22 | 2025-12-08 | 17
| Evaluate team using Brightspace survey | Not Started |  | 2025-12-01 | 2025-12-01 | 1
| Lonzo |  |  | 2025-11-17 | 2025-12-08 | 22
| # Add pytest unit tests for Profile, Schedule, Session, Flashcards, etc. | On Hold | SHA 45ab501, fe680ac | 2025-11-17 | 2025-11-17 | 1 | What is this use case's user story number? If no user story, make sure you add this as a user story in our final sprint.
Nov 26th: 29 commits, +483, -163
| Evaluate Dr. Edwards via Class Climate | Not Started |  | 2025-11-22 | 2025-12-08 | 17
| Evaluate team using Brightspace survey | Not Started |  | 2025-12-01 | 2025-12-01 | 1
| Robin |  |  | 2025-11-22 | 2025-12-08 | 17
| # Update README with 6 numbered, prioritized projects | On Hold | SHA 0228979, 837cc5e | 2025-11-25 | 2025-11-25 | 1 | What is this use case's user story number? If no user story, make sure you add this as a user story in our final sprint.
| #63 Create a driver that has an ASCII art welcome message | Complete | SHA 56be12d2, 323162d, 9ba3910 | 2025-11-25 | 2025-11-25 | 1 | 63
| #64 Update driver so it randomly creates 111 student profiles and then outputs the student(s) with the longest schedule | Complete | SHA ddd432a, e4bdef1, ad88e06, 692794b, 361fe18 | 2025-12-01 | 2025-12-01 |  | 64
| #66 Update the driver to randomly create 33 study sessions and successively remove those sessions from any 2 randomly selected profiles | Complete | SHA a32bb34, la25ea0, b5f81f1 | 2025-11-25 | 2025-11-25 |  | 66
| #65 Update the driver to randomly create 222 study sessions and then randomly select any 2 profiles to study the same study sessions | Complete | SHA 9a0006e, bb3955c, 2a65b0c | 2025-11-25 | 2025-11-25 |  | 65
| #78 As a developer, I want to identify and comment-out failing unit tests in the tests directory, so that the tests run to completion. | Complete | SHA 9e97b3f, 0ef341, 86b03dc | 2025-12-01 | 2025-12-01 |  | 78
| #79As a developer, I want to identify and comment-out any code in my driver that causes it to not print the start and end of the driver successfully to verify that the code can build and run in the CLI | Complete | SHA | 2025-12-01 | 2025-12-01 |  | 79
| #80 As a developer, I want to finish writing and organizing the Software Design Document (SDD), so that viewers of the repo have a reference for system architecture, class diagrams, workflows, and design decisions. | Complete | SHA | 2025-12-01 | 2025-12-01 |  | 80
Nov 26th: 36 commits, +337, -250
| Evaluate Dr. Edwards via Class Climate | Complete |  | 2025-11-22 | 2025-12-08 | 17
| Evaluate team using Brightspace survey | Not Started |  | 2025-12-01 | 2025-12-01 | 1
| Samuel |  |  | 2025-11-17 | 2025-12-08 | 22
| # create AutoCancelJob, FlashcardGenerator, InviteLogic, Profile, StudySession classes | On Hold | SHA d926e23, 10b580f | 2025-11-17 | 2025-11-17 | 1 | What is this use case's user story number? If no user story, make sure you add this as a user story in our final sprint.
Nov 26th: 30 commits, +461, -122
| Evaluate Dr. Edwards via Class Climate | Not Started |  | 2025-11-22 | 2025-12-08 | 17
| Evaluate team using Brightspace survey | Not Started |  | 2025-12-01 | 2025-12-01 | 1
Formulas:
Start Date = MIN([Start Date, row below]:F21)
End Date = MAX([End Date, row below]:G21)

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.
https://www.smartsheet.com/top-project-management-excel-templates?srsltid=AfmBOorM8KTqo0GkEazFKhVFp3ozfOh-BifeI1KKxQxM0WpR5p08gBRL